## Sheet 1
Table 1
| SD Aug 2026 | SD Oct 2026 | SD Dec 2026 | USM Feb 2027 | SD Mar 2027 | SD May 2027 | SD Aug 2027 | SD Oct 2027 | SD Dec 2027 | SD Mar 2028
Linac refurbishment | Enter RI section 28Juillet ASK ALGE access from tunnel | Modulator 0 and 3 tests | Modulator tests, 6th to 14th January
Free tunnel space | Tunnel space
Free mod hall space | Empty material linac, empty material vacuum 3 days needed | Faraday cage. Check with safety if ti can be reinstalled somewhere (date To Be Defined ?? Stock somewhere in a way that it can be reinstalled)
Install waveguides | 10th to 19th august 14th August. Booster closure
Move containers | Find place for containers
Booster up | [8 empty] | Installation
LN2 | Plans. First Bertrand Pelissier then F. Favier |  | TBC: external works | TBC: external works | TBC: installation
Grounding | Start to Digg puits starting from 3rd to 12th August | Continue grounding installation. In 3 days possible to plant, but must restart in case of stone | Continue grouding installation
Water cooling | plans + start water installation | Continue water installation |  |  |  |  | Connect C-band
Temporary water cooling | Plans | Continue water installation | Take water from existing modulator. From both modulators.,
mono-Cranes | Plans for installation of crane (Sband) or pont rulant (3D) for both. |  |  | For S-band can be installed in end January or February (not during shutdown)
Holes in tunnel | Plans |  | drilling 17 Dec au 6 Jan Waveguides, cable tray, chiller, LN2 , laser DURING CLOSURE?
Cryomodule SLAC | [6 empty] | Installation
S-band RF unit |  |  | Installation
C-band RF-unit | [6 empty] | Installation
Electrical works | start | Continue | Continue, connect S-band |  |  |  | Connect C-band
RF waveguides | Plans |  |  |  | Installation (TBC) | Installation (TBC) | Installation (TBC)
Linac Tunnel HLS |  | Installation of protection coffin for the integral le ngth