## Sheet 1 - Operational use of CO
Operational use of COLD project linac
| charge beam (nC) | Charge dark cur (nC) | Rep rate | Hours of use | TOTAL yearly charge nC (assuming 4µs pulse) | MAX Energy | stage | Description of hours of use
2026 | 0 | 0 | 0 | 0 | 0 | 0
2027 | 0 | 1 | 4Hz | 2880 | 165.888 | 0-150 MeV | Phase 0 | Conditioning 3 month 24/24 h + 8h per day for the resting 3 month
2028 | 0.7 | 1 | 4Hz | 720 | 70.5024 | 0-350 MeV | Phase 1 | Test of Phase 1. Experiments for 2h/day for 12 month
2029 | 0.7 | 1 | 4Hz | 1260 | 123.3792 | 350 MeV | Phase 1 | Test of Phase 1. Beam commissioning (8h/day) for 3 month + experiments for 2h/day for 9 month
2030 | 0.7 | 0 | 4Hz | 2160 | 87.0912 | 350 MeV | Phase 2 | Test of Phase 2. Conditioning 3 month 24/24 h (only dark currents).
| 0.7 | 1 | 4Hz | 1080 | 105.7536 | 351 MeV | Phase 3 | Test of Phase 2. Beam commissioning for 3 month. Experiments for 2h/day for 6 month
2031 | 0.7 | 1 | 10Hz | 720 | 70.5024 | 350 MeV | Phase 2 | 12 month of 2h operation per day (experiments)
2032 | 0.7 |  | 4Hz | 2052 | 82.7366 | 350 MeV | Linac injector in SY | Commissioning (3 month 8h/day), time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2033 | 0.7 |  | 4Hz | 1332 | 53.7062 | 350 MeV | Linac injector in SY | Time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2034 | 0.7 |  | 4Hz | 1332 | 53.7062 | 350 MeV | Linac injector in SY | Time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2035 | 0.7 |  | 4Hz | 1332 | 53.7062 | 350 MeV | Linac injector in SY | Time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2036 | 0.7 |  | 4Hz | 1332 | 53.7062 | 350 MeV | Linac injector in SY | Time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2037 | 0.7 |  | 4Hz | 1332 | 53.7062 | 350 MeV | Linac injector in SY | Time for injection in SR (180h, 2min per hour), MDT (4days per month for 12 month)
2038 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2039 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2040 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2041 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2042 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2043 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2044 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2045 |  |  | 4Hz |  |  | 6GeV | 6GeV linac
2046 |  |  | 4Hz |  |  | 6GeV | 6GeV linac